## Plan
Phase | Sub-Phase | Task | Person-in-Charge | Remark | done | 202309 | 202310 |  |  |  | 202311 |  |  |  | 202312 |  |  |  | 202401 |  |  |  | 202402 |  |  |  | 202403
[6 empty] | week4 | week1 | week2 | week3 | week4 | week1 | week2 | week3 | week4 | week1 | week2 | week3 | week4 | week1 | week2 | week3 | week4 | week1 | week2 | week3 | week4 | week1 | week2 | week3 | week4
Touchpoint Integration | Integration Scope Confirmation | Get Touchpoint Table List from NGSE Team | Saikat+Faisal | Current TP table List provided by Bose, Saikat is based on NGSE Aug Release. List may be revised based on future releases.
| Data Integration | Global DDP >> HK Server | Global DDP | Only transfer China Data | bar: 202310 week2 to 202310 week4
|  | HK Server >> China DDP | China ZTD | / | bar: 202310 week2 to 202310 week4
| Data Quality Check Record Level + Column Level | Call | China ZTD + SFE | 1. Check whether backend tables have full China Data. If not, whether business team should maintain additional data records ; 2. Check whether columns used by NGSE have related content | bar: 202311 week1 to 202311 week2
Event | bar: 202311 week3 to 202311 week4
Account | bar: 202312 week1
Discussion | bar: 202312 week2
Asset | bar: 202312 week2
Campaign - use Wechat Mini Program data source | bar: 202312 week3 to 202401 week4
Product_Adoption - Future Use | bar: 202402 week1 to 202402 week4
Potential - be applied in China in 2024
Email/Case/Opportunity/Survey_Response
| Data Maintenance (optional) | Maintain Additional Data in Touchpoint | SFE | If there is data missing in Data Quality Check phase, then maintain additional data in Touchpoint
DDP Data Restructure | DDP Table Scope Confirmation | Get DDP Table List from NGSE Team | Saikat+Faisal | 1. Restructure required tables on China DDP 2. Generate sample data on China DDP 3.Assessment Report + Scorecard
| Data Restructure + Data Quality Check | Sales Data Restructure | China ZTD + Faisal + Global DDP
Customer Related Master
Product Related Master
Territory Related Master | bar: 202309 week4 to 202310 week1
Sales Representative Master | bar: 202311 week1 to 202311 week2
Sales Organization Master | bar: 202311 week3 to 202311 week4
Contract Related - to be check with Business Team | bar: 202312 week1 to 202312 week2
Front-End Enhancement | Function Module Replacement | Check Data Lack from Data Side | China ZTD + Faisal | For current NGSE modules that not applicable for China Market (eg Opportunity, Survey_Response), may need to use another module (eg Reference Lab) to replace | bar: 202311 week1 to 202311 week2
|  | Check Data Lack from Business Side | China ZTD + SFE | bar: 202311 week3 to 202311 week4
|  | Check NGSE Front-End Module Influenced by Lack of Data | Vince | bar: 202312 week3 to 202312 week4
|  | Check with Local Business Team about module replacement | China ZTD + SFE | bar: 202401 week1 to 202401 week4
| Function Module Enhancement | Collect Business Requirement | China ZTD + SFE | Based on Business requirements about adding new functional modules to NGSE China, check data readiness | bar: 202402 week1 to 202402 week4
Environment Set-up | Databricks | Databricks Set-up | China ZTD + Faisal | / | bar: 202309 week4 to 202310 week3
| Github | Github Set-up | bar: 202309 week4 to 202310 week3
| TP POC | TP POC - Using Call as Example | bar: 202309 week4 to 202310 week3
Data Readiness Report | 1st Round Scorecard | Data Readiness Draft Report | China ZTD + Vince | /
| 2nd Round Scorecard | Data Readiness Final Report | bar: 202312 week3 to 202312 week4; 202403 week1 to 202403 week4

## DDP Generated Table List
Revised DDP | Remark | Applicable for China
dim_Contract | Aug Release add | Not Known - DX Specific, talking to Jessie
dim_Customer |  | Y
dim_Market_Code |  | Y - Copy from Global DDP
dim_Product |  | Y
dim_Sales_Organization | Aug Release add | Pending confirmation from Global DDP
dim_Sales_Representative |  | Y
dim_source_Customer |  | Y
dim_Source_Product |  | Y
dim_Territory |  | Y
dim_TP_Account_Position |  | Y
fact_Account_Position |  | Y
fact_Contracts_Signed | Aug Release add | Not Known - DX Specific, talking to Jessie
rpt_Currency_Conversion_Rate |  | N - shown in CNY
rpt_Customer_GSA_Hierarchy | Aug Release add | Y - GSA setting in SFDC
rpt_fact_Direct_Sales_FFE_Intl | Aug Release add | N - Direct Sales
rpt_Species_Alloc_Aligned_Sls |  | Y
rpt_Species_Alloc_Aligned_Sls_FRA_Weekly | Aug Release add | N - France Specific

## TP Integration Table List
Touchpoint New List | Remark | Applicable for China
account |  | Y
asset |  | Y
attendee |  | Y
brand_indication | Aug Release add | Future use - Product Adoption (Product Name)
call |  | Y
campaign |  | N - Campaign data will come from Wechat Mini Program
campaign_member |  | N - Campaign data will come from Wechat Mini Program
case |  | N - Currently no China Data
competitor_product | Aug Release add | Future use - product adoption profiles, pending confirmation about whether applicable for China
contact |  | Y
et4ae5__IndividualEmailResult | Aug Release add | Not Known - Pending data integration to check
eu_account_position |  | Y
eu_account_species_potential |  | Y - Potential be applied in China in 2024
eu_discussion | Aug Release add | Discussion Item
eu_employee_call_credit | Aug Release add | Call owner and Credit Info
eu_position |  | Y
eu_species |  | Y
eu_species_product | Aug Release add | Event Product details
Opportunity | Aug Release add | N
product_adoption_profile | Aug Release add | Future use - product adoption profiles, pending confirmation about whether applicable for China
product_barrier | Aug Release add | Future use - product adoption profiles, pending confirmation about whether applicable for China
Survey_Response__c | Aug Release add | N - not applied in China, only have the yearly sample data
us_event_account |  | Y
us_event_product | Aug Release add | Not Known - Pending data integration to check
user |  | Y
ZTS_Events__c |  | Y